Work Breakdown Structure: Six Weeks to Prototype and Poster

Rule-Constrained Reinforcement Learning for Ambiguity-Aware IT Incident Triage

Opol Charis  |  S24B23/003  |  BSc Computer Science

Purpose. This document breaks the remaining work into packages and tasks, from the mid-semester milestone to the working prototype, research poster and evaluation evidence due in about six weeks. Effort figures are planning estimates in working days and should be adjusted after Week 1. Weeks are numbered from the first Monday after the milestone.

1. Six weeks at a glance

| Week | Focus | Work packages | Days | Milestone at end of week | Evidence |
| --- | --- | --- | --- | --- | --- |
| 1 | Collect scenarios; start the simulator | 1, 2, 3 | 6.8 | M1: Draft scenario model complete; simulator generates incidents | Scenario spreadsheet; code repository; sample incidents |
| 2 | Finish simulator; rule checker; first comparison strategies | 3, 4, 5 | 6.8 | M2: Scenario model frozen after staff review; three simple strategies run end to end | Review notes; test report; first metrics table |
| 3 | Train the agent; finish comparison strategies | 3, 5, 6 | 6.8 | M3: Trained DQN agent (10 seeds) with and without the rule checker | Learning curves; saved models; configuration files |
| 4 | Main comparison and ablations | 7 | 4.8 | M4: Results for Experiments 1 to 3 | Results tables with confidence intervals |
| 5 | Worse evidence; analysis; start the prototype | 7, 8 | 5.3 | M5: Robustness results (Experiment 4); replay screen working | Robustness charts; prototype screenshot |
| 6 | Prototype, poster and write-up | 8, 9 | 5.8 | M6: Working prototype, poster and results chapter ready | Demo; poster PDF; Chapter 4 draft |

2. Work breakdown structure

| ID | Work package / task | Deliverable | Week | Days | Depends on |
| --- | --- | --- | --- | --- | --- |
| 1 | Project management and approvals | Project stays on plan and within agreed terms | 1-6 | 3.0 |  |
| 1.1 | Sign the confidentiality agreement with the Directorate; confirm ethics requirements with the supervisor | Signed agreement; note of ethics position | 1 | 0.5 |  |
| 1.2 | Set up the code repository, folder structure and a weekly progress log | Repository with README and log | 1 | 0.5 |  |
| 1.3 | Weekly supervisor check-in and plan update (six sessions) | Dated log entries; updated plan | 1-6 | 2.0 |  |
| 2 | Scenario elicitation with the Directorate | Scenario model: 25 causes, 20 checks, 10 rules | 1 | 2.5 | 1.1 |
| 2.1 | Prepare the elicitation template: causes, first symptoms, checks and their cost, rules, and how likely each check is to be positive for each cause | Template (spreadsheet) | 1 | 0.5 |  |
| 2.2 | Run the elicitation session(s) with Directorate staff across the four categories: database, network, authentication, storage | Completed template; session notes | 1 | 1.0 | 1.1, 2.1 |
| 2.3 | Write up the scenario model: causes and fixes, checks, likelihood table, incident context attributes, ten rules | Scenario model v1 (configuration files) | 1 | 1.0 | 2.2 |
| 2.4 | Contingency, only if input is late (about half a day): draft the model from own knowledge and the literature, marked provisional | Provisional model | 1 | 0.0 | 2.1 |
| 3 | Incident simulator | Tested simulator with controllable ambiguity | 1-3 | 6.5 | 2.3 or 2.4 |
| 3.1 | Install and check the tools: Python, Gymnasium, Stable-Baselines3 | Working environment; requirements file | 1 | 0.5 | 1.2 |
| 3.2 | Incident generator: draw a hidden cause and context, generate first symptoms and the true result of every check | Generator module | 1 | 1.0 | 2.3 or 2.4 |
| 3.3 | Environment: evidence vector, 46 actions (20 checks, 25 fixes, 1 hand-over), rewards, step limit | Gymnasium environment | 1 | 1.5 | 3.2 |
| 3.4 | Three ambiguity controls: missing evidence, wrong evidence, overlapping causes | Configurable ambiguity levels | 2 | 1.0 | 3.3 |
| 3.5 | Reference labels: mark each incident as resolvable or one that should be handed over | Label function | 3 | 0.5 | 3.3 |
| 3.6 | Tests: unit tests, a random strategy and a strategy that knows the cause, to confirm the simulator behaves sensibly | Test report | 2 | 1.0 | 3.3 |
| 3.7 | Staff review of generated incidents; revise; freeze the scenario model before any training | Review notes; frozen model v2 | 2 | 1.0 | 3.6, 2.2 |
| 4 | Rule checker | Independent checker with review-then-hand-over | 2 | 2.0 | 3.3 |
| 4.1 | Encode the ten rules as readable conditions in a configuration file | Rules file | 2 | 0.5 | 2.3 |
| 4.2 | Wrapper: allowed goes ahead; blocked returns to the agent once; blocked again hands over; log every block | Checker module; block log | 2 | 1.0 | 4.1 |
| 4.3 | Tests for each rule and for the two-block path | Test report | 2 | 0.5 | 4.2 |
| 5 | Comparison strategies and measurement | Four simple strategies and a metrics module | 2-3 | 2.5 | 3.3, 4.2 |
| 5.1 | Guess from first symptoms; fixed checklist; always hand over | Three strategy modules | 2 | 0.5 | 3.3 |
| 5.2 | Act when confident enough: track the probability of each cause, check until one is likely enough, otherwise hand over | Threshold strategy module | 3 | 1.0 | 3.3 |
| 5.3 | Metrics module and evaluation runner: fixed set of evaluation incidents; decision quality, cost of checks, hand-overs, rule compliance | Metrics module; first results table | 2 | 1.0 | 3.3, 4.2 |
| 6 | Agent training | Trained agents and learning curves | 3 | 5.0 | 3.7, 4.3 |
| 6.1 | DQN agent wired to the simulator and rule checker, with the blocked action removed from the next choice | Training script | 3 | 1.0 | 4.2 |
| 6.2 | Pilot runs: fix the reward values, the base ambiguity level and the training length | Pilot notes; fixed settings | 3 | 1.0 | 6.1 |
| 6.3 | Small search over learning rate, network size and exploration | Chosen settings (recorded) | 3 | 1.0 | 6.2 |
| 6.4 | Train the proposed agent with 10 random seeds | Ten saved models; learning curves | 3 | 1.0 | 6.3 |
| 6.5 | Train the two learning comparisons: agent with no rule checker; agent with penalties only | Saved models; learning curves | 3 | 1.0 | 6.3 |
| 7 | Experiments and analysis | Evaluation evidence for the poster and Chapter 4 | 4-5 | 8.0 | 5.3, 6.4, 6.5 |
| 7.1 | Experiment 1: proposed agent against the six strategies at the base ambiguity level | Main results table | 4 | 1.0 | 6.4, 6.5 |
| 7.2 | Experiment 2: effect of the rule checker (attempted rule breaks over training; rule-compliant correct fixes) | Compliance table and chart | 4 | 1.0 | 6.5 |
| 7.3 | Experiment 3: train and test two cut-down agents, one that cannot check further and one that cannot hand over | Ablation table | 4 | 1.5 | 6.3 |
| 7.4 | Sensitivity: repeat Experiment 1 with a lower and a higher cost of handing over | Sensitivity table | 4 | 1.0 | 7.1 |
| 7.5 | Experiment 4: all strategies across the levels of each ambiguity control, one at a time and together | Robustness charts | 5 | 1.5 | 7.1 |
| 7.6 | Analysis: means with 95% confidence intervals; decision-mix charts; findings against the three hypotheses | Figures; findings summary | 5 | 1.5 | 7.1-7.5 |
| 7.7 | Optional, only if ahead of plan: repeat Experiment 1 with PPO; train with randomised ambiguity | Extra results | 5 | 0.5 | 7.1 |
| 8 | Working prototype | Demonstrable prototype | 5-6 | 3.0 | 6.4 |
| 8.1 | Replay screen: show one incident step by step (checks and results, proposals, blocks, final decision) | Replay screen | 5 | 1.5 | 6.4 |
| 8.2 | Results panel: comparison tables and charts beside the replay | Results panel | 6 | 1.0 | 7.6 |
| 8.3 | Demo script and run-through on a clean machine | Demo checklist | 6 | 0.5 | 8.1, 8.2 |
| 9 | Poster and write-up | Poster and results chapter | 6 | 4.0 | 7.6 |
| 9.1 | Draft Chapter 4: implementation and results | Chapter 4 draft | 6 | 1.5 | 7.6 |
| 9.2 | Update Chapters 1 to 3 with the elicitation details and the final settings | Revised chapters | 6 | 0.5 | 6.2, 3.7 |
| 9.3 | Research poster: problem, gap, pipeline, results, limits | Poster PDF | 6 | 1.5 | 7.6 |
| 9.4 | Archive code, configuration files and evaluation incidents; rehearse the presentation | Archive; rehearsal done | 6 | 0.5 | 8.3, 9.3 |

Total planned effort: 36.5 working days over six weeks (about 6.1 days a week). Task days within each package add up to the package figure. Weeks 1 to 3 are planned at close to seven days each, so they include weekend work; Weeks 4 to 6 are lighter and act as a buffer.

3. Critical path

Scenario model (2.3) → environment (3.3) → staff review and freeze (3.7) → DQN training (6.1 to 6.4) → Experiment 1 (7.1) → analysis (7.6) → poster (9.3). A delay in any of these delays the poster. The rule checker (4), the simple strategies (5) and the prototype screen (8.1) can proceed in parallel with them.

4. Risks and what to cut first

| Risk | Effect | Response |
| --- | --- | --- |
| Directorate input arrives late in Week 1 | Simulator and everything after it slip | Start with the provisional model (2.4) and replace it at the staff review (3.7). Agree this fallback with the supervisor first. |
| Agent does not learn, or always hands over | No meaningful results in Week 4 | Use the pilot runs (6.2) to adjust reward values and the base ambiguity level; check the simulator with the simple strategies before blaming the agent. |
| Training takes longer than a week | Experiments squeezed | Cut in this order: optional task 7.7, then random seeds from 10 to 5, then the joint ambiguity sweep in 7.5. |
| Confidentiality limits what can be shown | Poster or demo cannot show real rules | Describe scenarios and rules in generalised form; keep specifics out of the poster and archive. |

Not to be cut: the simulator, the DQN agent, the rule checker, the six comparison strategies and the four measures. These are what the milestone summary promised.